| Group Policy & Procedure | Document No. | P-POL-014 |
| --- | --- | --- |
| Group Supply Chain | Ver. No. ¦ Rev Date | 0.4 ¦ 08 APR 2026 |
| Title: Contract Management | Effective Date | 08 April 2026 |

BUKHATIR GROUP

Strength through Diversity

Group Policy and Procedure

Group Supply Chain (GSC)

Contract Management

Lifecycle, Register & Close-out

Document No: P-POL-014

Copyright © 2026 Bukhatir Group

# Revision Control

This document is issued under the authority of Bukhatir Group and applies when carrying out the activities described. Revisions may be issued as necessary under the authority of the Group Head of Procurement. Revision history is recorded below with every revised policy.

## Revision History

| Ver. No. | Effective Date | Description |
| --- | --- | --- |
| 02 | September 2016 | Original Procurement Policy |
| 0.3 | March 2026 | Procurement Policy – Contract Management |
| 0.4 | 08 April 2026 | Redesign, content modernization & flowcharts – Contract Management |

## Revision Sign-Off

| Approving Committee | Name | Signature |
| --- | --- | --- |
| Endorsed by — Group Head of Supply Chain | Mohamad Koussa |  |
| Reviewed by — BIIL CEO | Mr. Ayman Ismail |  |
| Reviewed by — Group Chief Financial Officer | Mohamad Adnaan Sait |  |
| Approved by — Group Vice Chairman & Group CEO | Mr. Salah Bukhatir |  |

## Distribution List

| # | Departments |
| --- | --- |
| 1 | Business Unit Procurement Departments |
| 2 | Group Supply Chain (GSC) |
| 3 | Finance, Legal, Compliance, Internal Audit |
| 4 | Business Unit Management |

# 1. Purpose

This policy defines how contracts are drafted, reviewed, executed, administered and closed across Bukhatir Group, ensuring legal enforceability, value realisation and risk control throughout the contract lifecycle.

# 2. Scope

Applies to all contracts with third parties for the supply of goods, services, works and sub-contracts, including framework agreements and NDAs.

# 3. Contract Lifecycle Stages

| Stage | Key Activities | Owner |
| --- | --- | --- |
| 1. Planning | Identify need, draft scope, risk assessment | BU + GSC |
| 2. Drafting | Select template, populate commercial & legal terms | GSC + Legal |
| 3. Negotiation | Commercial & legal negotiation, redlines | GSC + Legal |
| 4. Approval | DOA routing and sign-off | Per DOA |
| 5. Execution | Signature, archive in Contract Register | GSC |
| 6. Administration | Performance, amendments, claims, renewals | GSC + BU |
| 7. Close-out | Final acceptance, warranty release, lessons learned | BU + GSC |

# 4. Standard Templates

Legal maintains a library of approved templates: Purchase Order T&Cs, Services Agreement, Works Contract, Framework Agreement, NDA, MoU and LOI. Deviations require Legal review.

# 5. Contract Register

GSC maintains a central Contract Register capturing: contract reference, counterparty, value, start/end dates, renewal options, owner and status. The Register is the single source of truth for all active contracts.

# 6. Amendments & Variations

WRITTEN ONLY All amendments, variations, extensions and terminations shall be in writing and approved per DOA. Verbal changes are not enforceable and shall not be actioned.

# 7. Performance Monitoring

Contract owners shall review performance against contractual KPIs at least quarterly. Material breaches are escalated to GSC and Legal.

# 8. Close-out

On expiry or completion, GSC performs a formal close-out: final deliverables accepted, warranty retention released (where applicable), lessons learned captured and the Contract Register updated.

# 9. Reference Forms

- Form F-CM-01 — Contract Request & Intake Form

- Form F-CM-02 — Contract Amendment / Variation Form

- Form F-CM-03 — Contract Close-out & Lessons Learned Form

# 10. Definitions & Acronyms

| Acronym / Term | Definition |
| --- | --- |
| AED | United Arab Emirates Dirham |
| BU | Business Unit |
| DOA | Delegation of Authority |
| GSC | Group Supply Chain |
| KPI | Key Performance Indicator |
| MoU | Memorandum of Understanding |
| NDA | Non-Disclosure Agreement |
| Oracle | Enterprise Resource Planning System |
| SLA | Service Level Agreement |
| T&Cs | Terms and Conditions |